## Sheet1
11/06-11/19 - User Stories | Task | Story Points | Checkout | Status | sprint backlog | Ready | In-Progress | Done | Finish Date
1. BugFixing | Figure out the Bugs | 5 | Erik | Ready |  |  | x
| Sleeping Bug | 5 | Rami | Ready |  |  | x
| Fixing Bugs | 5 | Erik | Ready |  | x
2.Continue working on Temporary Silencing | Implementing the integration of Settings | 3 | Rami | Ready |  | x
3.Continue working on a Clear Settings menu | Create On/Off functionality | 5 | Alon | Ready |  |  | x
4. Ability to edit a location's settings | Fix up ListView UI | 1 | Thomas | Ready |  | x
| Connect Listview and settings activity | 2 | Thomas | Ready |  | x
| Add versioning for setttings | 5 | Thomas | Ready |  |  | x
| Fixing up settings ui logic | 2 | Thomas | Ready |  | x
5. Graphic Development | Create Icon | 2 | Alon | Ready |  | x
6. Real World Testing | Test different functionalities | 5 | Everyone | Blocked | x
7. Computer Vision | Computer vision | 8 | Erik | Blocked | x